## In-flight
38 |  |  | Please dont update this summary columns. These are auto pupulated from individual sections. | [6 empty] | Project Health Drivers | [8 empty] | Timelines RAG | [13 empty] | V360 Milestones |  |  |  |  | Ramp Milestones | [5 empty] | Challenges, Risks, Mitigations & Action Plan | [5 empty] | 8
Customers / Projects | Segment / POD | Project Manager | Project Health RAG | V360 RAG | Ramp RAG | Ramp ARR | Current Stage | Current GoLive | Current Unlock | Scope / Reqments | Schedule | Budget | Quality | Resources | Steerco in Place | Customer Sentiment | Current Stage | Prj Health | Baseline Go-live | Project Start | Design End | Realize/FUT End | FUT Pass % | SIT Start | SIT End | SIT Build | SIT Pass % | UAT Start | UAT End | UAT Build | UAT Pass % | Go-live | Value Succ Criteria defined | Baselining Completed | V360 reporting | Value Architect | V360 Status | Contracted Unlock Date | ARR | RAMP ARR | Ramp Criteria | Current Unlock Date | Status | Risks & Dependencies (only Top 3) | Mitigation Plan (Risk/ unlock Ramp) | Mitigation Owner | Mitigation Date | Go to Green Plan if overall is red/amber | Date To Green | PM Review Done?
Adura Shell ¦ mInventory ¦ Implementation | Gold | Gnana Lalitha Rupini Miriyala | Green | N/A | N/A | N/A | Hypercare | 2026-04-06 | N/A | Signed-Off | Green | Green | Green | Green | N/A | Green | Hypercare | Green | 2026-04-10 | 2025-09-15 | 2025-10-17 | 2026-01-16 |  |  | 2026-02-13 |  |  |  | 2026-03-06 |  | 100% | 2026-04-06 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes
Airgas ¦ mWO + RDF + mINV ¦ S4 HANA Upgrade Support | Diamond | Akshay Khandave | Green | N/A | N/A | N/A | Test - SIT | 2026-04-23 | N/A | Signed-Off | Green | Green | Green | Green | On Demand | Green | Hypercare | Green | 2024-04-12 | 2023-12-18 | N/A | 2026-02-20 | Closed in past |  | 2026-03-27 |  |  |  | 2026-04-14 |  |  | 2026-04-23 | N/A | N/A | N/A | N/A | N/A | N/A | 482568 | N/A | N/A | N/A | N/A | None | None | None | None | None | None | Yes
Airgas Canada ¦ mWO + mINSP + mINV ¦ Implementation | Diamond | Sai Deepak Chevendra | Green | N/A | N/A | N/A | R - FUT | 2026-10-05 | N/A | Signed-Off | Green | Green | Green | Green | On Demand | Green | R - FUT | Green | 2026-10-05 | 2026-03-02 | 2026-04-10 | 2026-05-11 |  | 2026-04-27 | 2026-05-29 |  |  | 2026-05-11 | 2026-09-02 |  |  | 2026-10-05 | N/A | N/A | N/A | N/A |  | N/A |  | N/A | N/A | N/A | N/A | * Need to have email access for performing FUT of PR/PO approval test scripts.This might lead to delay in performing and closing FUT on time.This will lead to delays in executing the tests and could impact the timely completion and closure of the FUT process. *Airgas need to deploy latest hotfix in SD1 inorder for the localization to function in Canada environment for mInventory without many notable issues. | * Following up with Luis for resolution of email issue. *Following up with Luis and Yanping for latest hotfix deployment | *Luis *Luis, Zubair | *04-May-26 *04-May-26 | N/A | N/A | Yes
CEER Motors ¦ mAssetTag ¦ Implementation | Gold | Bhamidipati Avinash | Green |  | N/A | N/A | Test - SIT | 2026-04-27 | N/A |  | Amber | Green | Green | Green |  | Green | Test - SIT | Green | 2025-09-26 | 2025-05-26 | 2026-03-06 | 2026-03-13 |  |  | 2026-03-27 |  |  |  | 2026-04-17 |  |  | 2026-04-27 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | 1. The device for the UAT are to be confirmed by the client. Current Go-Live date is moved to 27-Apr-26. | Client has raised the request for device procurement and currently the request is pending with Ceer Motors's Chief Executive team for approval. ETA- 6-Mar-26 - No Update from the client yet. Revised ETA-14-Apr-26 |  |  |  |  | No
Chobani ¦ mWO + RDF + mInv + VP ¦ Implementation | Diamond | Sai Deepak Chevendra | Green | N/A | N/A | N/A | Deploy | 2026-04-15 | N/A | Signed-Off | Green | Green | Green | Green | N/A | Green | Deploy | Green | 2026-04-22 | 2026-02-04 | 2026-02-18 | 2026-03-23 |  |  | 2026-03-30 |  |  |  | 2026-04-03 |  |  | 2026-04-15 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Yes
Cenovus Energy ¦ mWO + mRO ¦ Support | Gold | Deeptam Mukherjee | Green | N/A | N/A | N/A | Design | 2027-01-04 | N/A | Signed-Off | Green | Green | Green | Green | N/A | Green | Design | Green | 2027-01-04 | 2026-03-16 | 2026-04-27 | 2026-05-04 |  |  | 2026-05-25 |  |  |  | 2026-11-23 |  |  | 2027-01-04 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Yes
Dyno Nobel ¦ mWO + mINSP + mRO ¦ Implementation | Platinum | Kavya Prabhukumar | Green | Green | Green | 239778 | R - FUT | 2026-07-07 | 2026-10-01 | Signed-Off | Green | Green | Green | Green | Yes | Green | R - FUT | Green | 2026-06-29 | 2026-01-26 | 2025-07-25 | 2026-04-13 | mWO - 95% mR - 100% | N/A | 2026-05-08 | NA | NA | 2026-05-11 | 2026-06-11 | TBD | Yet to Start | 2026-07-07 | 2026-03-20 | 2026-03-16 | 2026-07-06 | Bharath Ganapathy Chowrira | Green | NA |  | 239778 |  | 2026-10-01 | Green | 1. Penetration Testing, the Division 5 team would need to perform the PEN testing as a part of CAB approvals. 2. The PoV assessment is planned for eight weeks; however, there is a risk that the business may require additional time (1–2 months) to complete the evaluation. The SOW includes a clause for an additional subscription fee of AUD 25K per month (capped at two months), which could impact overall ramp-up value and financial planning if timelines extend beyond the planned period. | 1. Establish a clear timeline and PEN testing process. Alignment with internal stake holders on defect resolution timeline and team availibility. Fast-track issue resolution to prevent delays to Golive. 4. Lock success criteria and scope of the PoV by end of March to ensure alignment on measurable outcomes and exit criteria. Establish regular governance forums with business stakeholders to track progress, escalate delays, and reaffirm adherence to agreed timelines. | Krishna Oza Kavya Prabhukumar | 2026-06-25 |  |  | Yes
Electranet ¦ mWO 2.0 + mINSP ¦ Implementation | Diamond | Kavya Prabhukumar | Red | N/A | N/A | N/A | R - Config | 2026-11-02 | N/A | Signed-Off | Red | Green | Green | Green | Yes | Green | R - Config | Red | 2026-07-15 | 2025-10-13 | 2026-03-20 | 2026-09-14 | Yet to start | Planning in progress | Planning in progress | Planning in progress | Yet to start | Planning in progress | Planning in progress | Planning in progress | Yet to start | 2026-11-02 | N/A | N/A | N/A | Bharath Ganapathy Chowrira | N/A | N/A |  | N/A | N/A | N/A | N/A | DEPENDENCY- 1. On Enet (Tenant setup & SCAR DB – May 8) and Custom logic – May 29 2. ETA from Inno Product team for 17 GAP items. RISK- 1. Any delay from Enet on tenant setup or custom logic delivery or potential internal slippage from the Innovapptive P&I team, may impact overall project timelines | 1.Secured firm dates from Enet (May 8 – Tenant setup & SCAR DB, May 29 – Custom logic) 2.Re-engaged the Innovapptive P&I team to provide ETAs aligned with the revised timelines. Alignment with Engineering leadership is in progress to ensure delivery adherence. Current ETA is mid-August, contingent on no further slippage in Electranet timelines 3.Initiated engagement with Dyflex (call on April 30); shared packages and running working sessions to expedite DEV setup by May 8 4.Finalize and publish revised project plan once ETAs are confirmed | Tim Hartnett (Electranet) Murali( Inno P&I) Dyflex/FT Team Kavya | 1. 08 May (Tenant Setup) & 29th May (Custom logic development) 2. 15th Aug (Inno P&I Development) 3. 08 May (Dev Setup) 4. 15th May (Publish Revised Project Plan) | 1. Align with all stakeholders (ENet, Diplex, Product team) to obtain firm timelines and close open dependencies. 2. Prioritize critical path items (SAP developments, API licenses, product fixes) and fast-track through focused follow-ups and escalation where required. 3. Re-baseline timelines if required and ensure continuous monitoring with proactive risk mitigation. | 2026-05-08 | Yes
Grace ¦ mWO + mINSP + mRO + mINV ¦ (Lake Charles) Rollout | Platinum | Bhamidipati Avinash | Green | Green | Green | 44286 | Hypercare | 2026-04-06 | 2026-07-01 |  | Green | Green | Green | Green |  | Green | Hypercare | Green | 2025-11-28 | 2025-09-08 | [11 empty] | 2026-04-06 |  |  |  | Rafael Gijon | Green |  |  | 44286 |  | 2026-07-01 | Green | NA | NA |  |  |  |  | No
Hexion ¦ mWO 2.0 + mINS + mRO ¦ Implementation | Platinum | Akshay Khandave | Amber | Amber | Amber | 168340 | Design | 2026-09-18 | 2026-12-04 | In Progress | Green | Green | Amber | Green | Yes | Green | Design | Amber | 2026-09-14 | 2026-02-02 | 2026-05-01 | 2026-05-29 | To be started | 2026-06-01 | 2026-07-31 | To be started | To be started | 2026-08-03 | 2026-09-11 | To be tested | To be tested | 2026-09-18 | 2026-03-24 | 2026-05-21 | 2026-09-28 | Chris Grau | Amber | 2026-07-01 |  | 168340 | Demonstrate value realization 3 times of 'Proof of investment' | 2026-12-04 | Amber | Risk: Integrated Product Development Description: iPermit and DWI products are not yet integrated with the CWP platform. Original planned date is 04/15 Issue: Delayed design phase Details: Delayed BRD sign-off due to pending approvals from customer, pending alignments with gensuite integration requirement, preparing SDD draft with internal reviews Action: PS team enablement for iPermit and DWI | Product integration: P&I to provide the integrated product release. Status: At Risk. Revised date is 04/20 > 05/05 (At risk) Delayed design phase: PS SC team to work with customer and own BRD, SDD review and sign-off PS team enablement for iPermit and DWI: Rajasekhar Grandhi, Shaun Ezekiels to validate PS readiness, conduct KT sessions and product testing to get hands on | Product integration: Surya Swethan Pothula (iPermit), Neeharika Avula (DWI) Delayed design phase: Rajasekhar Grandhi, Shaun Ezekiels iPermit and DWI enablement: Rajasekhar Grandhi, Shaun Ezekiels | Product integration: Status: At Risk. Revised date is 04/20 > 05/05 (At risk) Delayed design phase: 04/30 > 05/08 iPermit and DWI enablement: 04/29 > 05/05 | * As mentioned in risk, dependencies and mitigation plan | 2026-05-05 | Yes
Huntsman ¦ mWO 2.0 + mINSP + mINV + mRO ¦ Implementation | Diamond | Deeptam Mukherjee | Amber | N/A | N/A | N/A | Design | 2026-08-31 | 2026-09-30 | Signed-Off | Green | Green | Green | Green | Yes | Green | Design | Amber | 2026-07-20 | 2026-02-23 | 2026-04-28 | 2026-06-01 | Have Time | 2026-06-08 | 2026-07-20 | Have Time | 0% | 2026-07-27 | 2026-08-10 | 2603.01 |  | 2026-08-31 | 2026-03-20 | 2026-03-27 | 2026-07-10 | Chris Grau | N/A | 2026-09-30 |  | N/A | N/A | 2026-09-30 | N/A | 1. Unavailability of integrated products (DWI) with iCWP platform 2. BTP is procured and now with Accenture team to check and confirm on the API. | 1. DWI Web is available to start the progress a sper the plan. 2. BTP is in place, and Greg has responded with the entitlement details. The item is currently with the Accenture team to review whether the Integrated Suite falls within BTP. At this stage, the status is Amber. We expect confirmation on Monday, after which the status will be reviewed. If the API is not managed under BTP, this will be considered a risk and the status may change to Red next week. | 1. Neeharika Avula 2. Arun & Merrilly (Accenture) | Product Integration: 04/20 > 05/05 BTP API Integration: 05/04 | As per the mentioned risk, if the agreed dates are achived , Its a green go status. | 2026-05-08 | Yes
Husky Energy ¦ mWO + mRO ¦ Implementation | Platinum | Deeptam Mukherjee | Green | N/A | N/A | N/A | Plan | 2026-09-30 | N/A | Not Started | Green | Green | Green | Green | Yes | Green | Plan | Green | 2026-09-30 | 2026-03-31 | 2026-05-20 | 2026-06-17 |  |  | 2026-08-05 |  |  |  | 2026-09-02 |  |  | 2026-09-30 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | [6 empty] | Yes
Idaho Asphalt ¦ mWO 2.0 + mINSP ¦ Implementation | Gold | Sri Karthik | Green |  | N/A | N/A | Hypercare | 2026-04-20 | N/A | Signed-Off | Green | Green | Green | Green |  | Green | Hypercare | Green | 2026-05-01 | 2026-01-19 | 2026-02-06 | 2026-03-13 |  |  | 2026-03-27 | 2511.01(616) | 0% |  | 2026-04-10 | 2603.01 |  | 2026-04-20 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | [6 empty] | Yes
Indorama Ventures ¦ mWO + RDF + mInv + mRO ¦ Phase 2 Rollout | Platinum | Shashi Podeti | Green | Green | Green | 649758 | Hypercare | 2025-12-17 | 2026-12-01 | Signed-Off | Green | Green | Green | Green | Yes | Green | Hypercare | Green | 2025-10-06 | 2025-02-10 | 2025-10-17 | 2025-10-17 |  |  | 2025-10-24 |  |  |  | 2025-12-05 |  |  | 2025-12-17 |  |  | 2025-09-08 | Rafael Gijon | Green |  |  | 649758 |  | 2026-12-01 | Green | * CS transition taking longer than usual | * Open actions discussed with CSM and being actioned, suppport to respond on the blockers for them to transition. | Joseph | TBD | NA | NA | Yes
JK Cement ¦ mWO 2.0 + mINSP ¦ Implementation | Gold | Rahul Inwate | Amber | N/A | Amber | 25905 | Test - UAT | 2026-05-20 | 2026-07-17 | Signed-Off | Amber | Amber | Red | Green | Yes | Amber | Test - UAT | Amber | 2025-12-26 | 2025-07-07 | 2026-02-19 | 2026-03-06 | 87% | 2026-03-05 | 2026-03-13 | 2602.01(778) | 97% | 2026-04-17 | 2026-05-08 | 2603.01 |  | 2026-05-20 | N/A | N/A | N/A | Deepak Kumar Bharati | N/A | 2026-06-01 |  | 25905 |  | 2026-07-17 | Amber | 1. Regression from UAT execution (includes issue slip enhancement) 2. JKC requested to move to DMS changes from GOS (JKC is ok to plan after go live) 3. JKC(maintenance heads) brought up 3 new requirements and cited these to be delivered before we plan for the go live on May 20th | 1. PS & P&I have to focus on absolute UAT exit blockers and provide the fix ETA/workarounds agreeable to JKC by May 12th 2. JKC and Innovapptive need to work together for completing the config. Estimation timeline of 3 weeks 3. PS is working with P&I to understand the possible workarounds for these requirements and also plan the sizing for estimation. There's an external alignment discussion with JKC & Innovapptive team on May 08th. | 1. Deepak / Deependra 2. Praveen (JK Cement)/ Rahul I 3. Rahul, Vasu & Praveen (JKC) | 04/04 > 04/13 > 04/15 >05/12 06/10 (DMS) 05/08 | JKC project will be green post comleting the go live. | 2026-05-20 | Yes
Kimberly Clark ¦ mWO + mINSP + mINV ¦ Pilot Implementation | Platinum | Praveen Barry | Green | Green | Green | 619000 | Hypercare | 2026-02-09 | 2026-06-01 |  | Green | Green | Green | Green | Yes | Green | Hypercare | Green | 2025-09-26 | 2025-06-23 | 2025-09-12 | 2025-10-24 | N/A |  | 2025-12-12 |  |  |  | 2026-01-23 |  |  | 2026-02-09 | 2025-06-10 | 2026-02-05 | 2026-03-16 | Vishal Srivastava | Green | 2025-11-01 |  | 619000 |  | 2026-06-01 | Green | * Migration to CS with respect to the product details, client have been done, checklist shared with the team for the final review. * Site Visit Feedback and Findings, KC HUNTS/MAU, analysis completed, PCR draft in-progress | * Finial version of the checklist has been updatedto, review from CS team and approval pending. * PS team to review and update the pending details ASAP. | Joseph Rajashekar | 05/05 05/04 |  |  | Yes
Landmarc ¦ mWO 2.0 + mINSP ¦ Implementation | Platinum | Praveen Barry | Red | Amber | Amber | 143750 | Design | 2026-07-06 | 2026-12-01 | Signed-Off | Amber | Green | Red | Amber | No | Green | Design | Red | 2026-02-13 | 2025-10-13 | 2026-04-30 | 2026-05-15 | To be commenced | 2026-05-11 | 2026-05-29 | 2603.01 | To be commenced | 2026-06-08 | 2026-06-19 | 2603.01 | To be commenced | 2026-07-06 | 2026-04-24 | 2026-05-08 | 2026-08-03 | Shouvitra Dasgupta | Amber | 2026-11-02 |  | 143750 |  | 2026-12-01 | Amber | *The build scheduled for 24 April release to the PS team is still pending, blocking progress. * Landmarc Dev instance readiness, planned for 30-Apr, is delayed by 2–3 days, pushing FUT and impacting overall project timelines. * The offline sync service, a key component of the solution, is currently unavailable as the Ditto team has withdrawn support going forward. | * The issues identified in the current build are being addressed along with the open items as per the BRD by 05/08; * The team has created an Azure DevOps dashboard to track infrastructure setup activities; Dev instance readiness is expected by 05/04. * Product team is evaluating alternative options and will provide a final recommendation along with a revised delivery plan by 6 May 2026. | 1. Santhosh Chilakalapudi, Sandeep Jha & Rahulkrishnan Chandrasekharan are responsible for item 1. 2. Glenn (Landmarc) 3.Santhosh Chilakalapudi & Rahulkrishnan Chandrasekharan | 04/24 > 05/08 for product dependecies 04/17 > 04/30> 05/04 for infra rediness based on the client interactions 05/06 | The mentioned risks must be addressed by the agreed dates to achieve a "Green" status. | 2026-04-30 | Yes
Lotte Chemical ¦ mRO + mINV ¦ Implementation | Diamond | Shashi Podeti | Amber | N/A | N/A | N/A | Hypercare | 2026-05-05 | N/A | Signed-Off | Amber | Green | Amber | Green | N/A | Amber | Hypercare | Amber | 2026-04-20 | 2023-10-02 | 2023-02-28 | 2024-02-06 | NA | NA | 2024-03-01 | NA | NA | NA | 2024-03-06 | NA | NA | 2026-05-05 | N/A | N/A | N/A | Rafael Gijon | N/A | N/A |  | N/A | N/A | N/A | N/A | Asset mismatch validation failing repeatedly | Joseph looking into the issue to resolve | Joseph | 2026-05-04 | [04/21-SKP]:Once Joseph is able to mitigate the asset mismatch issue, Ely will need to validate the system and move ahead with going live | 2026-04-27 | Yes
Mohawk ¦ mAssetTag ¦ Implementation | Gold | Sai Deepak Chevendra | Green |  | N/A | N/A | On-hold | 2026-07-24 | N/A |  | Green | Green | N/A | Green |  | Green | On-hold | Green | 2026-08-07 | 2026-03-30 | 2026-04-24 | 2026-05-22 | [6 empty] | 2026-07-10 |  |  | 2026-07-24 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | [6 empty] | No
Nyrstar ¦ mWO 2.0 + mINSP ¦ Implementation | Gold | Akshay Khandave | Green | N/A | N/A | N/A | Test - SIT | 2026-06-08 | N/A | Signed-Off | Amber | Green | Amber | Green | Yes | Green | Test - SIT | Green | 2026-05-18 | 2025-06-30 | 2026-03-13 | 2025-12-10 | Completed in past | 2025-12-15 | 2026-05-08 | 2602.01(778) | 85% | 2026-04-27 | 2026-05-29 | To be tested | To be tested | 2026-06-08 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Issues: Delayed system re-setup post SAP refresh is impacting SIT retesting & closure Risk: Nyrstar team's availability to start UAT is impacting overall timeline | * PS FT team and Engineering team to release system to PS functional on 05/01 * Nyrstar to confirm dates for training and UAT (Delayed since Nyrstar POC is on leave) | * Kushagra * Akshay, Himanshu, Jo Janssen | * 05/01 * 05/05 | * As mentioned in risk, dependencies and mitigation plan | 2025-04-28 | Yes
Origin Energy ¦ mInventory ¦ Implementation | Gold | Kavya Prabhukumar | Green | N/A | N/A | N/A | R - FUT | 2026-06-04 | N/A | Signed-Off | Green | Green | Green | Green | No | Green | R - FUT | Green | 2026-05-22 | 2025-11-10 | 2026-02-24 | 2026-04-17 | 80% | 2026-04-20 | 2026-05-01 | Yet to be decided | Yet to start | 2026-05-11 | 2026-05-22 | Yet to be decided | Yet to start | 2026-06-04 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | SPCC improvements to be delivered before Go live | Product team to provide delivery dates | Santhosh Chakrawarthy Kanna | 2026-05-25 |  |  | Yes
PBF Energy ¦ mInventory ¦ Toledo Rollout | Gold | Sai Deepak Chevendra | Green | N/A | N/A | N/A | Test - SIT | 2026-06-01 | N/A | Signed-Off | Green | Green | Green | Green |  | Green | Test - SIT | Green | 2026-06-01 | 2026-03-30 | 2026-04-10 | 2026-04-24 |  | 2026-04-24 | 2026-05-05 |  |  | 2026-05-11 | 2026-05-20 |  |  | 2026-06-01 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | *Innovapptive hasn’t been given necessary access permissions that are required for successful execution. In the event of issues during testing, timelines may be impacted due to Innovapptive’ s lack of direct system access, making coordination and resolution dependent on multiple teams *Milestones might be delayed if any issues occur. Innovapptive doesn’t have enough level of access and need to coordinate with multiple teams in case of any issues. | *Conveyed the same to PBF and took an approval from their end. *Conveyed the same to PBF in form of an email. | * Sai Deepak, Cassandra *Sai Deepak, Himanshu, Cassandra | *20 May *6 June | N/A | N/A | Yes
Sabert Corporation ¦ mWorkOrder ¦ Upgrade | Gold | Rahul Inwate | Green | Green | N/A | N/A | Deploy | 2026-03-31 | N/A | Signed-Off | Green | Green | Green | Green |  | Green | Deploy | Green | 2025-05-09 | 2025-02-03 | 2026-01-23 | 2025-04-29 |  |  | 2025-05-13 |  |  |  | 2026-02-24 |  |  | 2026-03-31 |  |  |  |  | Green | N/A |  | N/A | N/A | N/A | N/A | Post completion of the deploy phase, need to monitor any regression observed on iOS & Windows. | PS & P&I to review and come up ETA for any regression identified during the Hyper care phase. | * Kalyan & Vijay Sharma | * 06th May |  | 2026-03-31 | Yes
Santos ¦ mRounds ¦ Implementation | Platinum | Kavya Prabhukumar | Amber | Green | N/A | N/A | Design | 2026-08-25 | N/A | In Progress | Green | Green | Amber | Green | No | Green | Design | Amber | 2026-08-17 | 2026-03-23 | 2026-05-08 | 2026-06-12 | TBC | 2026-06-15 | 2026-06-17 | TBC |  | 2026-07-20 | 2026-08-14 |  |  | 2026-08-25 | In Progress |  |  | Bharath Ganapathy Chowrira | Green | 2026-08-15 |  | N/A | N/A | N/A | N/A | 1. mRounds Task Limit: 350–400 task cap may impact performance for large rounds 2. Design Phase Closure: New gaps may delay design sign-off and downstream phases | 1. Discussion with the product team on the strategy of to optimize/shorten task 2. Fast-track gap closure and align on scope/decisions quickly | 1. Abhijit Maharana 2. Markus - Santos | 1. 28 Apr 2. 4 May | 1. Finalize mRounds solution with product team and confirm timelines 2. Align with Santos to unblock gap sign-off and close design phase 3. Implement interim design measures (split rounds, optimize data) 4. Lock pilot scope and continue technical readiness activities | 2026-05-08 | Yes
SaskPower ¦ mInventory ¦ S4 Hana Support | Gold | Praveen Barry | Green |  | N/A | N/A | Hypercare | 2025-06-09 | N/A |  | Amber | Green |  | Green |  | Amber | Hypercare | Green | 2025-06-02 | 2024-05-27 |  | 2024-09-30 |  |  | 2024-11-13 |  |  |  | 2025-04-25 |  |  | 2025-06-09 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | - Issue with respect to TO confirmation module, HU blocked- Innovapptive provided the fix for the issue, moved to the QA, | client to verify in QA and move the changes to production. | Savitha, SaskPower | 1. 15-MAy |  |  | Yes
Shell ¦ mInventory ¦ (Nigeria) Rollout | Gold | Gnana Lalitha Rupini Miriyala | Green | N/A | N/A | N/A | Test - SIT | 2026-06-15 | N/A | Signed-Off | Green | Green | Green | Green | NA | Green | Test - SIT | Green | 2026-09-11 | 2026-02-02 | 2026-02-20 | 2026-04-17 | NA | 2026-03-30 | 2026-04-10 |  | 92% | 2026-04-27 | 2026-05-29 |  |  | 2026-06-15 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes
Shell P31 ¦ mInventory ¦ Implementation | Gold | Gnana Lalitha Rupini Miriyala | Green | N/A | N/A | N/A | Test - UAT | 2026-05-18 | N/A | Signed-Off | Green | Green | Green | Green | N/A | Green | Test - UAT | Green | 2026-05-22 | 2025-11-03 | 2025-11-19 | 2026-03-02 |  |  | 2026-03-31 |  |  |  | 2026-04-24 |  | 100% | 2026-05-18 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes
SMG ¦ mWO 2.0 + mINSP + mRO + mINV ¦ Implementation | Diamond | Akshay Khandave | Green | Amber | Green | 224150 | Test - SIT | 2026-06-22 | 2026-08-28 | Signed-Off | Green | Green | Amber | Amber | Yes | Green | Test - SIT | Green | 2025-11-28 | 2025-07-07 | 2025-10-16 | 2025-10-24 | N/A | 2025-10-27 | 2026-05-15 | 2502.01 (778) | 57% | 2026-05-18 | 2026-06-12 | To be tested | To be tested | 2026-06-22 | 2026-03-20 | 2026-04-16 | 2026-04-27 | Chris Grau Vishal Srivastava | Amber | 2025-12-01 |  | 224150 | Under negotiation. Contract states: 2-Months post pilot and acheiving criteria of $300K annualized cost savings | 2026-08-28 | Green | Risk: Visual Planner Implementation Delay Description: Pending closure of the revised contract is impacting the start of the implementation. | Visual Planner: Pradeep M. is working on getting the contract signed. PS team to align with Solution Engineering to ensure implementation starts by 04/02 > 04/10 > 04/17 | * Contract revision - Pradeep Menon, Sean Matteson | * Contract revision - 04/10 > 04/17 > 04/28 | * As mentioned in risk, dependencies and mitigation plan | 2026-04-28 | Yes
Tabreed ¦ mRounds ¦ Implementation | Gold | Sundeep Ankisetty | Green |  | N/A | N/A | Test - SIT | 2026-05-29 | N/A |  | Green | Green |  | Green |  | Green | Test - SIT | Green | 2026-04-24 | 2026-01-12 | 2026-03-02 | 2026-04-15 |  | 2026-04-15 | 2026-05-08 |  |  |  | 2026-05-18 |  |  | 2026-05-29 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | [6 empty] | No
Tafisa ¦ mWorkOrder ¦ Upgrade | Gold | Bhamidipati Avinash | Green |  | N/A | N/A | Hypercare | 2026-03-29 | N/A |  | Green | Green | Green | Green |  | Green | Hypercare | Green | 2025-12-12 | 2025-09-22 | 2026-03-06 | 2026-02-27 |  |  | 2026-03-06 |  |  |  | 2026-03-13 |  |  | 2026-03-29 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | No
Torex Gold ¦ mAT + mINV ¦ Implementation | Gold | Gnana Lalitha Rupini Miriyala | Amber | N/A | N/A | N/A | Hypercare | 2026-03-17 | N/A | Signed-Off | Green | Green | Amber | Green | Yes | Green | Hypercare | Amber | 2025-05-16 | 2025-01-06 | 2025-10-24 | 2025-11-18 |  |  | 2026-01-09 |  | 100% |  | 2026-02-27 |  | 100% | 2026-03-17 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Recurring regression defects: Each hotfix (HF) or fix release is causing previously stable functionalities to break, posing a risk to overall system stability and release quality for localisation. | The P&I team has agreed on a relase timeline for week of 4th May on localisation fixes. | Santhosh Chakrawarthy Kanna | 2026-05-04 | N/A | N/A | Yes
Tronox ¦ mInventory ¦ (Yanbu) Rollout | Gold | Bhamidipati Avinash | Green |  | N/A | N/A | Hypercare | 2025-09-11 | N/A |  | Green | Green | Green | Green |  | Green | Hypercare | Green | 2025-10-10 | 2025-07-14 |  | 2025-08-08 |  |  | 2025-08-15 |  |  |  | 2025-09-05 |  |  | 2025-09-11 | N/A | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | N/A | Client's team SPOC to present the Value360 Dashboard to the leadership. Delay in the presentation is impacting the closure | Client is working on the updated deck which is planned to be presented to their leadership by 2nd Week of April. |  |  |  |  | No
Tronox ¦ mInventory ¦ Implementation | Gold | Bhamidipati Avinash | Green |  | N/A | N/A | Hypercare | 2025-05-19 | N/A |  | Green | Green | Green | Green |  | Green | Hypercare | Green | 2025-05-16 | 2024-09-02 | 2024-12-06 | 2025-05-02 |  |  | 2025-05-14 |  |  |  | 2025-05-13 |  |  | 2025-05-19 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | Client's team SPOC to present the Value360 Dashboard to the leadership. Delay in the presentation is impacting the closure | Client is working on the updated deck which is planned to be presented to their leadership by 2nd Week of April. |  |  |  |  | No
Tronox ¦ mInventory ¦ Stallingborough & Thann Rollout | Gold | Bhamidipati Avinash | Green |  | N/A | N/A | Design | 2026-07-10 | N/A |  | Green | Green | Green | Green |  | Green | Design | Green | 2026-05-08 | 2026-02-16 | 2026-03-27 | 2026-05-10 |  |  | NA |  |  |  | 2026-05-22 |  |  | 2026-07-10 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | No Major Risks in the project | N/A |  |  |  |  | No
UNICEF ¦ mAssetTag ¦ Upgrade PCR | Platinum | Akshay Khandave | Amber | N/A | N/A | N/A | Test - UAT | 2026-05-08 | N/A | Signed-Off | Red | Green | Amber | Green | On Demand | Amber | Test - UAT | Amber | 2025-08-15 | 2025-05-12 | 2025-05-28 | 2025-07-21 | Closed in past | Closed in past | 2025-08-08 | N/A | N/A |  | 2026-05-01 |  |  | 2026-05-08 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Issue: Not receiving required approvals from customer Description: Due to misalignments between Innovapptive and UNICEF for UAT scope, it was agreed that UNICEF to review and approve FSD and test scripts. But even after multiple reminder, didn't receive required response from UNICEF. It was communicated on 04/21 that Innovapptive offboarded resources and project is put on hold until UNICEF confirms they are ready | Mitigation Activity: UNICEF to provide approval for revised FSDs and test script required for UAT and confirm when UNICEF team is available and ready to dedicate time for project activities | * UNICEF Team: Shankar | 04/03/2026 > 04/10/2026 > TBD | * As mentioned in risk, dependencies and mitigation plan | TBD | Yes
UNICEF ¦ mRounds ¦ Implementation | Platinum | Sai Deepak Chevendra | Green | N/A | N/A | N/A | Test - UAT | 2026-05-13 | N/A | Signed-Off | Green | Green | Green | Green | On Demand | Green | Test - UAT | Green | 2026-05-15 | 2025-12-22 | 2026-04-13 | 2026-03-13 | Closed in past |  |  |  |  | 2026-04-17 | 2026-05-04 |  |  | 2026-05-13 | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | None | Yes
Westlake ¦ mRO + mINSP ¦ (13 addl. Sites) Rollouts | Platinum | Rahul Inwate | Green |  | N/A | N/A | Deploy | 2026-06-19 | N/A |  | Amber | Green | Red | Green | Yes | Amber | Deploy | Green | 2025-12-05 | 2025-05-12 | 2026-05-14 | [7 empty] | 2026-02-23 |  |  | 2026-06-19 | [5 empty] | N/A |  | N/A | N/A | N/A | N/A | *IP21 issues and changes affecting the go live for the remaining sites. *Environment stability is a concern after every refresh. | *IP21 changes are planned to move to PRD by 02nd June. * P&I has to avoid the release deployment during the planned go live dates. | 1.Varaprasad Yerramsetti Sunil Methari Ranjith 2 Ranjith | 1. 02nd June | Post deployment of the IP21solution to PRD, remaining go live dates will be confirmed by the Westlake team. | 2026-04-17 | Yes
Wilmar Sugar ¦ mWO + mINSP + mRO + mINV ¦ Implementation | Platinum | Kavya Prabhukumar | Green | Red | N/A | N/A | Hypercare | 2026-04-06 | N/A | Signed-Off | Green | Green | Green | Red | No | Green | Hypercare | Green | 2025-02-10 | 2024-04-01 | 2024-08-06 | 2024-09-16 | Closed | Closed | 2024-10-11 | #2862 | 100% | 2026-02-11 | 2026-03-04 | mWO - 2862 | 100% | 2026-04-06 | TBC | 2026-05-15 | 2026-05-22 | Bharath Ganapathy Chowrira | Red | 2026-04-15 |  | N/A | N/A | N/A | N/A | Duplicate or inconsistent confirmations require control at source and in posting logic Status and field inconsistencies affect execution confidence End-to-end validation under real conditions has some gaps | Wilmar to provide the list of critical items/scope for cure period Cure acceptance criteria and governance cadence | Vijay Kumar Sharma Babumiya Mohammad Prateek Ketkar | 2026-06-03 |  |  | Yes
Formulas:
Current GoLive = [Go-live]

## Upcoming
Key Staffing
Customers / Projects | Segment / POD | Overall Prep Status | Deal Closure Date | ROM Completed? | SoW Sign Off Date | Sales to PS Transition | Project Start Date | Baseline Prj Plan Date | Staffing Finalised | PD | PM | SC | FTC
3M Company ¦ mWO 2.0 + mINSP + mINV + mRO ¦ Implementation | Platinum | Green | 2026-06-30 | No | 2026-06-30 | 2026-06-23 | 2026-07-17 | 2026-06-23 | No | Sean Matteson | TBD | TBD | TBD
Solstice ¦ mWO 2.0 + mINSP + mINV + mRO ¦ Implementation | Platinum | Green | 2026-05-15 | No | 2026-05-15 | 2026-05-08 | 2026-06-01 | 2026-05-08 | No | Sean Matteson | TBD | TBD | TBD
Westlake ¦ mRounds ¦ (25 Sites) Rollouts | Platinum | Green | 2026-05-08 | No | 2026-05-08 | N/A | 2026-05-04 | 2026-05-01 | No | Himanshu Tripathi | Rahul Inwate | TBD | TBD
Indorama Ventures ¦ mWO + RDF + mInv + mRO ¦ Phase 3 Rollout | Platinum | Green | 2026-05-15 | No | 2026-05-15 | N/A | 2026-06-01 | 2026-05-08 | No | Sean Matteson | Shashi Podeti | TBD | TBD
Field Name | OpenAir? | OpenAir Field Name
Customers / Projects | Yes
Segment / POD | Yes | POD
Project Manager | Yes
Project Health RAG | Yes
V360 RAG | Yes
Ramp RAG | Yes
Ramp ARR | Yes
Current Stage | Yes
Current GoLive | Yes
Current Unlock | Yes
Scope / Reqments | No
Schedule | Yes
Budget | No
Quality | Yes
Resources | Yes
Steerco in Place | Yes
Customer Sentiment | Yes
Current Stage | Yes
Prj Health | Yes
Baseline Go-live | Yes | Planned Go-live Date
Project Start | Yes
Design End | Yes | Design Date
Realize/FUT End | Yes | FUT Date
FUT Pass % | No
SIT Start | No
SIT End | Yes | SIT Date
SIT Build | No
SIT Pass % | No
UAT Start | No
UAT End | Yes
UAT Build | No
UAT Pass % | No
Go-live | Yes
Value Succ Criteria defined | No | Success Criteria Defined
Baselining Completed | No | Baselining Completed
V360 reporting | No | V360 Reporting
Value Architect | No | Value Architect
V360 RAG | Yes | V360 RAG
Contracted Unlock Date | No | Contracted Unlock Date
ARR | No | ARR
RAMP ARR | Yes
Ramp Criteria | No | Ramp Criteria
Current Unlock Date | Yes
RAMP RAG | Yes | Ramp RAG
Risks & Dependencies (only Top 3) | Yes | Critical Risk
Mitigation Plan (Risk/ unlock Ramp) | Yes | Mitigation Plan
Mitigation Owner | Yes
Mitigation Date | Yes
Go to Green Plan if overall is red/amber | Yes
Formulas:
SoW Sign Off Date = [Deal Closure Date]
Sales to PS Transition = [SoW Sign Off Date]-7
Project Start Date = [SoW Sign Off Date]+(7*2)+3
Baseline Prj Plan Date = [SoW Sign Off Date]-7

## SIT Progress (hidden)
JK Cement Progress
Target date | 13th March
SIT Exit critieria | 90% successful Test script execution No high and highest bugs
OS | Test Cases | [5 empty] | Issues Stats
| Target # | Pass # | Fail # | Pending # | Pass % | Fail % | Highest # | High # | Medium #
Android | 65 | 63 | 2 | 0 | 96.92% | 3.077% |  | 3 | 1
iOS | 65 | 63 | 2 | 0 | 96.92% | 3.077%
Nrystar Progress
Target date
SIT Exit critieria
OS | Test Cases | [5 empty] | Issues Stats
| Target # | Pass # | Fail # | Pending # | Pass % | Fail % | Highest # | High # | Medium #
Android | 75 | 21 | 8 | 38 | 28% | 10.67% |  | 3
iOS | 75 | 0 | 2 | 73 | 0% | 2.667%
SMG Progress
Target date
SIT Exit critieria
OS | Test Cases | [5 empty] | Issues Stats
| Target # | Pass # | Fail # | Pending # | Pass % | Fail % | Highest # | High # | Medium #
Android | 75 | 21 | 8 | 38 | 28% | 10.67% |  | 3
iOS | 75 | 0 | 2 | 73 | 0% | 2.667%

## iCWP Standup Notes (hidden)
Summary/Workstream | Details | Customers | Expected release date | Release date | Open actions and help required | Release components | Comment | Status
Showstoppers from PS, & SE Testing (release 2602.01) | There are 5 issues | Idaho, NYR, SMG | 2026-03-18 | 03/18/2026 25/Mar/2026 - 2026.01.01 (Planned on 03/31) 27/Mar/26 - 2026.01.02 | Jira release page updated required SMG: - SIT retesting with build 778 in SMG system, provide list of blockers for phase exit. Kalyan and Nikhil. Due Date: 03/24 - Confirm resolution plan for renewable SIT exit blockers (hotfix). Owners: Dipendra and Vasudev. Due Date: 03/25 - Timeline to exit Innovapptive SIT: 04/03: Impacted due to issues faced in system setup after release 2602.01 and delayed SIT retesting by PS. Plan of action - need HF for exit blockers - Reference: JIRA Dashboard: https://innovapptive.atlassian.net/jira/dashboards/16441?maximized=50649 Nyrstar: - Confirm resolution plan for customer SIT exit blockers (hotfix). Owners: Dipendra and Vasudev. Due Date: 03/24 - For any alignment on customer SIT exit blockers, please coordinate with Nitesh and Zubair. - Timeline to exit customer SIT: 04/03: Impacted due to issues faced in system setup after release 2602.01, waiting for ad-hoc build (2026.01.01) which is delayed for more than a week. Plan of action - need HF for exit blockers as above mentioned - Reference: JIRA Dashboard: https://innovapptive.atlassian.net/jira/dashboards/16441?maximized=45921 | Build, no add-ons, cloud refresh | #03/17: Blocked due to a bug about WO closure postings and will impact release timeline #03/20: More blockers are identified by Sri. If need to include in this release, another build can be released by Thu. Two builds 03/23 and 03/26 #03/25: Resolution plan to be finalized on 03/27 #03/26: Resolution plan to be finalized on 03/27 (NYR) & 03/30 (SMG) #03/27: NYR HF scheduled on 04/07. SMG HF to be confirmed by 03/30
JKC Issue slip |  | JKC, Idaho | 2026-03-16 | Mar/25/2026 04/09/2026 | - Pending alignment - PS team to provide support for testing. Pending answers from Rahul I. to be closed by 03/17 - Work with Deepak for testing requirement in JKC system | Build, cloud refresh, add-ons (HANA) | 20/Mar: Delay from the customer could impact ETA of 24/Apr 03/23: * Blocked for DUT due to TR movement (action with JKC team). * Details required from JKC, issue slip tables don't have timestamps and need confirmation from JKC. Innovapptive will take 8 days to deliver (to be validated interanlly by engineering team) #03/25: Revised date 04/09 #03/26: Received required details from customer. Target date release - 04/09
Migration to Ditto |  | All | TBD | TBD |  |  | Meeting scheduled (03/17) with Mongo DB to review if we can get extension, if it happens, Ditto will be parked for Apr release and plan testing activities accordingly Received confirmed for extension till Jun 2026, engaged with partner for migration. Next actions: (1) Immediate focus: Upcoming builds to be shared with customers with RealM, fix issues corresponding to the same (2) Migration plan to be finalized - for PROD customers separately and non-PROD customers separately - TBD
Hexion system setup with separated S3 | * Interim build for public S3 is planned on 03/18 (completed as on 03/18) * Release of private S3 is pending. Can PS builid QA system with public S3 and later engg can migrate to private S3? | Hexion | 2026-03-12 | 03/27/2026 (2602.01.03) | 20/Mar: a new build on 23/Mar to make it private - System technical setup in Hexion environment. Status: At Risk Dependencies/Issues: S3 bucket separation (failed after building system in DEV (Jira ticket: SA2-1089) - Fixed) DEV system setup : 03/23 (Overdue because of issue identified) QA system target date: 03/27 (At Risk) |  | Migration required for other customers: Pending discussion with RD. Timeline to be aligned #03/26: On track for 03/26 | Closed
Product integration (iPermit & DWI) with iCWP |  | Hexion, Huntsman | 2026-03-30 | 04/15/2026 04/20/2026 |  |  | Mobile DWI: code merge - 31st Mar #03/25: Tracking green #03/26: iPermit - Vijay & DWI - Deependra
Release 2603.01 |  |  |  |  | 20/Mar Confirm the scope and ETA - Scope review and alignment completed with PS Solution Consulting and Solution Engineering teams to align on scope for the release. This includes reviewing improvements and new feature inclusions as part of the product roadmap and ensuring no regression impacts, as most projects will be entering customer testing cycles. Action owner: Vasudev, Deependra
Landmarc Ditto issues | * The build incorporating Ditto implementation and Reliability changes was initially scheduled for release on 28-Feb but was delayed and released on 11-Mar with blockers and app crashes. * Subsequently, the product team released another build, which still contained blockers and failed scenarios. * As committed, the product team is expected to provide a stable build on 06-Apr. --------------------------------------------------------------------------------------------- * Product team provided the build to PS team on 07-April, PS team started testing the application & identified sync & configuration issues. * Streamlining the build is priority to start the training sessions for Landmarc stakeholders. | Lanmdarc | 04/06/2026 04/09/2026 |  | * Streamlined build to be provided by the product team to start the training program. * Landmarc has scheduled the training session from 14-Apr, making a stable build by 09-Apr essential. * The financial closure for the Ditto license is yet to be completed and needs to be finalized |  | #03/25: QA team reported issues. PS testing is in progress. #03/26: Customer superuser training to be started 6th Apr. Ditto build will be used for Landmarc. #04/08: PS team reported issues, product team are fixing those issues.
Idaho FUT (2602.01.02) | Build used - #856 iOS & Android (interim build provided only for testing) All showstoppers are resolved as confirmed by Sri Pending - Funcational defects (around 10) - need timeline. Aman to provide details to Deependra & Vasu | Idaho | 2026-03-30 | 2026-03-30
Separated S3 migration | Customer specific is feasible, list of priorities for migration: * SMG - (P2) - migration plan is required * NYR - (P2) - migration plan is required * Hexion - Immediate need (P0) - start immediately with Kushagra & Nikhil * Idaho - (P1) - to be planned * JKC - (P1) - to be planned * Huntsman - No impact

## iCWP - Project Timelines - summ (hidden)
Project and activities | time axis 2026-03-30 to 2026-08-15
SMG | bar: 2026-04-10; 2026-04-13; 2026-04-20; 2026-06-22
Nyrstar | bar: 2026-04-24; 2026-04-27; 2026-05-22
Hexion | bar: 2026-04-27
JKC | bar: 2026-04-28; 2026-05-05; 2026-05-07 to 2026-05-08; 2026-05-14 to 2026-05-15
Landmarc | bar: 2026-04-27; 2026-05-08; 2026-05-11; 2026-05-22
P&I releases | bar: 2026-04-07; 2026-04-09; 2026-04-13; 2026-04-15 to 2026-04-16; 2026-04-20; 2026-05-05; 2026-05-08; 2026-05-15
🟢
🟢

## iCWP - Project Timelines (hidden)
Project and activities | time axis 2026-03-30 to 2026-08-15
SMG | bar: 2026-03-30 to 2026-08-15
FUT
SIT | bar: 2026-03-30 to 2026-05-01
UAT | bar: 2026-05-04 to 2026-06-12
Issues Fixes / Build Release from P&I | bar: 2026-04-09
Nyrstar
Important Milestones across Project
SIT | bar: 2026-03-30 to 2026-04-24
UAT | bar: 2026-04-27 to 2026-05-15
Issues Fixes / Build Release from P&I | bar: 2026-04-09; 2026-04-16; 2026-05-08
Hexion
Important Milestones across Project
FUT | bar: 2026-04-27 to 2026-05-29
SIT | bar: 2026-06-01 to 2026-07-27
UAT
Issues Fixes / Build Release from P&I | bar: 2026-04-15
Landmarc
Important Milestones across Project | bar: 2026-05-08; 2026-07-06
Training to Landmarc Users | bar: 2026-04-14; 2026-04-16; 2026-04-21 to 2026-04-22
FUT | bar: 2026-04-27 to 2026-05-08
SIT | bar: 2026-05-11 to 2026-05-22
UAT | bar: 2026-06-08 to 2026-06-19
Go-Live | bar: 2026-07-06
Issues Fixes / Build Release from P&I | bar: 2026-04-07
JKC
Important Milestones across Project | bar: 2026-04-30; 2026-05-05; 2026-06-02; 2026-06-16; 2026-06-23
FUT
SIT
UAT | bar: 2026-04-06 to 2026-04-30
Issues Fixes / Build Release from P&I | bar: 2026-04-13
Idaho
Important Milestones across Project
FUT
SIT
UAT
Issues Fixes / Build Release from P&I
Huntsman
Important Milestones across Project | bar: 2026-04-20; 2026-08-09
FUT | bar: 2026-06-01
SIT | bar: 2026-06-08 to 2026-07-20
UAT | bar: 2026-07-27 to 2026-08-07
Issues Fixes / Build Release from P&I | bar: 2026-04-20
Electranet
Important Milestones across Project
FUT
SIT
UAT
Issues Fixes / Build Release from P&I

## Accelerated Timelines
|  |  | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53
Project | Contracted Go-Live | Baseline Go-live | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
Planned P&I Releases | bar: 2026-04-20 to 2026-12-28
JKC |  | 2026-03-31
Current timeline |  |  | 2026-04-20: Training & UAT; 2026-05-11: Cutover & Go Live
Accelerated timeline |  |  | 2026-04-20: Training & UAT; 2026-05-11: Cutover & Go Live
Nyrstar | 2025-11-17 | 2026-06-08 | bar: 2026-04-20 to 2026-12-28
Current timeline |  |  | 2026-04-20: QA refresh; 2026-04-27: SIT Customer; 2026-05-18: Training preparation; 2026-06-01: Site downtime; 2026-06-15: Training & UAT; 2026-07-13: Cutover & GoLive
Accelerated timeline
Accelerated with buffer
SMG | 2025-10-13 | 2026-06-22 | bar: 2026-04-20 to 2026-12-28
Current timeline |  |  | 2026-04-20: SIT Customer; 2026-05-18: QA refresh; 2026-05-25: UAT; 2026-06-08: CAB & cutover; 2026-06-22: Go Live
Accelerated timeline |  |  | 2026-04-20: SIT Customer; 2026-05-18: QA refresh; 2026-05-25: UAT; 2026-06-08: CAB & cutover; 2026-06-22: Go Live
Accelerated with buffer
Huntsman |  | 2026-08-31
Current timeline |  |  | 2026-04-20: Design & config.; 2026-05-11: SAP; 2026-05-18: iCWP refresh; 2026-06-08: SIT Internal; 2026-07-06: SIT Customer; 2026-07-27: Training & UAT; 2026-08-31: Cutover & Go Live
Accelerated timeline |  |  | 2026-05-11: SAP; 2026-05-18: iCWP refresh; 2026-06-01: Unit testing; 2026-06-08: SIT Internal; 2026-06-22: SIT Customer; 2026-07-06: Training & UAT; 2026-07-20: Cutover & Go Live
Accelerated with buffer
Hexion |  | 2026-09-14 | bar: 2026-04-20 to 2026-12-28
Current timeline |  |  | 2026-04-20: Design & FUT; 2026-05-11: iCWP Refresh; 2026-05-25: SIT Internal; 2026-06-15: QA refresh; 2026-06-29: SIT Customer; 2026-07-13: QA refresh; 2026-07-27: Training; 2026-08-03: UAT; 2026-08-10: QA refresh; 2026-08-31: Cutover & Go Live
Accelerated timeline |  |  | 2026-05-11: iCWP Refresh; 2026-05-18: SIT Internal; 2026-06-01: SIT Customer; 2026-06-15: QA refresh; 2026-06-22: Training & UAT; 2026-07-06: Cutover & Go Live
Accelerated with buffer |  |  | 2026-04-20: Design, config, FUT; 2026-05-18: iCWP Refresh; 2026-05-25: SIT Internal; 2026-06-15: QA refresh; 2026-06-22: SIT Customer; 2026-07-13: QA refresh; 2026-07-20: Training; 2026-07-27: UAT; 2026-08-10: Go Live; 2026-08-17: QA refresh
Dyno |  | 2026-09-14
Current timeline |  |  | 2026-04-20: QA Refresh; 2026-04-27: Validation; 2026-05-04: Training; 2026-05-11: UAT; 2026-05-18: UAT; 2026-05-25: UAT; 2026-06-01: UAT; 2026-06-08: UAT; 2026-06-15: PEN; 2026-06-22: PEN; 2026-06-29: Cutover & Go Live
Accelerated timeline
Accelerated with buffer
Santos |  | 2026-09-14
Current timeline |  |  | 2026-04-20: Design; 2026-05-18: Realize (inc FUT); 2026-06-15: SIT Internal; 2026-06-29: Training; 2026-07-06: SIT Customer; 2026-07-20: UAT; 2026-08-17: Cutover & Go Live
Accelerated timeline |  |  | 2026-04-20: Design; 2026-05-18: Realize (inc FUT); 2026-06-08: SIT Internal; 2026-06-22: Training; 2026-06-29: UAT; 2026-07-27: Cutover & Go Live
Accelerated with buffer
Wilmar |  | 2026-09-14
Current timeline |  |  | 2026-04-20: Hypercare - Pilot site; 2026-05-18: Rollout to Remaining Sites
Accelerated timeline | bar: 2026-09-07 to 2026-12-28
Accelerated with buffer | bar: 2026-09-07 to 2026-12-28

## Test Summary
Project | Requirements | Test cases | Total issues | Unresolved issues | UAT Exit blockers
SMG | 28 | 32 | 192 | 27
NYR | 40 | 22 | 280 | 76
Hexion | 39 | 60 | 22 | 20
Huntsman | 28 |  | 5 | 5
JKC | 16 | 77 | 144 | 33
Project | Test Phase | Build | Start Date | End Date | Status | Test cases | Executed # | Pass % | Issues | Resolved | Unresolved | Blockers #
SMG | Innovapptive SIT | Build 661 |  |  | Completed | 28 | 100% | 53%
SMG | Innovapptive SIT | Build 778 |  | 2026-04-10 | Completed | 28 | 100% | 39% |  |  |  | 19
SMG | Innovapptive SIT | Build 949 |  | 2026-04-17 | Completed | 32 | 100% | 100% |  |  |  | 0
SMG | Customer SIT | Build 987 |  | 2026-05-15 | In Progress | 32 | 100% | 71%
JKC | Innovapptive SIT | Build 778 |  | 2026-03-05 | Completed | 130 | 100% | 87%
JKC | Customer SIT | Build 778 |  | 2026-04-03 | Completed | 130 | 100% | 97% |  |  |  | 3
JKC | UAT | Build 987 |  | 2026-05-12 | In Progress | 152 | 100% | 96% |  |  |  | 9
NYR | Customer SIT | Build 661 |  |  | Completed | 20 | 95% | 85% |  |  |  | N/A
NYR | Customer SIT | Build 778 |  | 2026-04-21 | Completed | 20 | N/A | 90% |  |  |  | 18
NYR | Customer SIT | Build 987 |  | 2026-04-28 | Completed | 20 | 100% | 95% |  |  |  | 0
Landmarc | FUT | Build 936 |  | 2026-04-13 | Completed | 35 | 100% | 79% |  |  |  | 5
Hexion | Innovapptive SIT - mRounds | Waiting for confirmation | 2026-05-26 | 2026-06-19 | In Progress | 59 | 41% | 24%
Hexion | Innovapptive SIT - iMaintenance | 1076 | 2026-05-26 | 2026-06-19 | In Progress | 61 | 33% | 18%